## Sheet1
Machine-readable travel document (MRTD)
Group C
| Group members: Ruchita Piathankar, Arun Rao Nayineni, Dhruv Patel |  | PROJECT START | 2023-04-24
|  |  | DISPLAY WEEK: | 0 |  | 2023-04-24 | [6 empty] | 2023-04-24 | [6 empty] | 2023-04-24
[6 empty] | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14
TASK NO. | TASK | ASSIGNED TO | PROGRESS | START | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1 | Requirements Testing
Task 1.1 | Identify any ambiguity in the current requirement specifications | Ruchita | 100% | 2023-04-24 | 2023-04-25 | bar: 2023-04-24 to 2023-04-27
Task 1.2 | Identify the key roles of stakeholders who should approve your plan. | Dhruv | 100% | 2023-04-24 | 2023-04-25 | bar: 2023-04-24 to 2023-04-27
Task 1.3 | Rewrite the requirement specification with details and clarifications | Arun | 100% | 2023-04-25 | 2023-04-27
Task 1.4 | Document the tasks | Dhruv | 100% | 2023-04-25 | 2023-04-27
Task 1.5 | Review and Submit | Ruchita | 100% | 2023-04-27 | 2023-04-28
Phase 2 | Unit Testing |  | 100%
Task 2.1 | Implement the functions for requirement specifications | Ruchita | 100% | 2023-04-28 | 2023-04-29
Task 2.2 | Write test cases to test each function implemented | Ruchita | 100% | 2023-04-29 | 2023-04-29
Task 2.3 | Write test cases to test each function implemented | Dhruv | 100% | 2023-04-30 | 2023-04-30
Task 2.4 | Write test cases to test each function implemented | Dhruv | 100% | 2023-04-30 | 2023-05-01
Task 2.5 | Write test cases to test each function implemented | Arun | 100% | 2023-04-30 | 2023-05-01
Phase 3 | Performance Testing
Task 3.1 | write a program to execute the program that measures the execution times | Arun | 100% | 2023-05-01 | 2023-05-02
Task 3.2 | Plot the data on x and y axes in the CSV file | Dhruv | 100% | 2023-05-01 | 2023-05-02
Task 3.3 | An explanation for the data plot | Ruchita | 100% | 2023-05-02 | 2023-05-02
Phase 4 | Test Planning
Task 4.1 | Describe the overall system and high-level goals,test strategy, approaches used and its impacts | Dhruv | 100% | 2023-05-02 | 2023-05-04
Task 4.2 | describe the relevant information available in the provided document | Ruchita | 100% | 2023-05-04 | 2023-05-05
Task 4.3 | Testing scope, what is being tested and what is not | Ruchita | 100% | 2023-05-01 | 2023-05-05
Task 4.4 | Define the Test Approach. Key factors, risks, contingency plans, etc. | Arun | 100% | 2023-04-28 | 2023-05-08
Task 4.5 | Prepare the timeline for key testing deliverables | Arun | 100% | 2023-05-01 | 2023-05-09